## Tabelle1
# | Task | Outcome
0. Kick-off | ▢ Create a new private Git repo called net-dash. | Place to build & run everything.
▢ Spin up a small Ubuntu Server VM on your hypervisor (1 vCPU, 1 GB RAM).
1. Inventory file | ▢ Make devices.csv with hostname,ip,location (3–5 home-lab boxes to start). | Single source of truth for targets.
2. Ping poller | ▢ Write poller.py that reads the CSV and pings each IP once. | You can run python poller.py and see rows appear.
▢ Log result (timestamp,host,latency_ms,up/down) to results.sqlite.
3. Automate polling | ▢ Add a cron job (*/5 * * * * python /path/poller.py). | Automatic 5-min checks.
4. Basic alerting | ▢ Write alert.py that scans the last 3 rows/host; if all “down”, send an e-mail (use Gmail SMTP test account). | You receive a “device offline” mail after ~15 min outage.
5. REST endpoint | ▢ Build a minimal Flask app (app.py) with /api/status that returns latest row per host in JSON. | Curl shows {"router":{"status":"up",...},...}.
6. Web dashboard v1 | ▢ Add / route that renders an HTML table with green/red dots and latency. (Use Bootstrap CDN for styling.) | Open browser → clean status table.
7. Containerise | ▢ Write a Dockerfile + docker-compose.yml that runs poller (sidecar) + Flask app. | docker compose up reproduces everything locally.
8. Deploy on VM | ▢ git pull on the Ubuntu VM. | Visit http://<vm-ip> on LAN; live dashboard loads.
▢ Install Docker & docker-compose.
▢ Run stack; map port 80 → 5000.
9. Docs & README | ▢ Add setup steps, .env sample, and a screenshot to README.md. | Anyone can replicate in < 5 min.
10. Weekly polish (optional) | ▢ SNMP CPU/RAM pull ➜ store to DB. | Stretch goals for extra résumé shine.
▢ Spark-line charts with Chart.js.
▢ Add .env secrets, proper logging, TLS via Nginx.